## Suite1
Environment : Stage Version : 7.0.327 Date : 15-01-2026
Smoke Scenarios | Status | Automation Status | Evidence | Owner | IBS Jira | Existing/New Jira | QA Comments |  | Automation Feature File | Remarks
Cruise Upload - Cabin Rate PP - (ADD,UPD,DEL),Download - Listing in UI | Pass | Yes
Cruise Upload - Cabin Rate OP - (ADD,UPD,DEL),Download - Listing in UI | Pass | No |  | Kavitha
Group Catalogue - Group listing and search | Pass | Yes | [6 empty] | group_SMK_TC_184_GroupCatlgListingAndSearch
Group Catalogue - Add Groups -On Option and Active- ADD,UPD | Pass | Yes | [6 empty] | group_SMK_TC_185_GroupAddOn_Option_Active_ADD_UPD_Cancel.feature
Group Catalogue - Groups - View, Modify | Pass | Yes | [6 empty] | group_SMK_TC_186_View_Modify.feature
Group Catalogue - Group Organiser- ADD, UPD | Pass | Yes | [6 empty] | group_SMK_TC_187_GroupOrganiser.feature
Group Catalogue - Group Agency details- ADD,UPD,DEL | Pass | Yes | [6 empty] | group_SMK_TC188_GroupAgencyDetails.feature
Group Catalogue - Group programs - Cruise - ADD,UPD,DEL | Pass | Yes
Group Catalogue - Group programs - AIR- ADD,UPD,DEL | Pass | Yes | [6 empty] | group_SMK_TC_190_Group_Program_AIR.feature
Group Catalogue - Group programs - Hotel- ADD,UPD,DEL | Pass | Yes |  | Greeshma |  |  |  |  | group_SMK_TC_191_Group_Program_Hotel.feature
Group Catalogue - Group programs - MISC- ADD,UPD,DEL | Pass | Yes | [6 empty] | group_SMK_TC_193_Group_Program_Misc.feature
Group Catalogue - Group programs - (mix and match) - ADD,UPD,DEL | Pass | Yes | [6 empty] | group_SMK_TC_194_Group_Program_Mix_Match.feature
Group Catalogue - Group controls-ADD,UPD | Pass | Yes |  | Greeshma |  |  |  |  | group_SMK_TC195_GroupControls.feature
Internal Air Setup - AIR - Create an internal air under an existing supplier and contract [Create an AIR Contract] | Pass | Yes | [6 empty] | air_SMK_TC156_InternalAIRSetupCreateAIRContract.feature
Internal Air Setup - AIR Taxes and Surcharges - Create a surcharge for AIR product | Pass | Yes | AirSur1601 | Greeshma |  |  |  |  | air_SMK_TC159_InternalAirSetupAIRTaxesAndSurcharges.feature
Internal Air Setup - AIR Settings - Verify AIR settings sceen, change values and save - Surcharge Configuration | Pass | Yes |  | Greeshma |  |  |  |  | air_SMK_TC160_TC_178_verifyAirSettingsScreen.feature
Internal Air Setup - AIR Settings - Verify AIR settings sceen, change values and save - Fare Rule Category | Pass | Yes |  | Greeshma |  |  |  |  | air_SMK_TC160_TC_178_verifyAirSettingsScreen.feature
Internal Air Setup - AIR Settings - Verify AIR settings sceen, change values and save - Fare Rules Configurations | Pass | Yes |  | Greeshma |  |  |  |  | air_SMK_TC160_TC_178_verifyAirSettingsScreen.feature
Internal Air Setup - AIR Settings - Verify AIR settings sceen, change values and save - Ticketing Time Limit | Pass | Yes |  | Greeshma |  |  |  |  | air_SMK_TC160_TC_178_verifyAirSettingsScreen.feature
Internal Air Setup - AIR Settings - Verify AIR settings sceen, change values and save - Air Shopping | Pass | Yes |  | Kavitha |  |  |  |  | air_SMK_TC160_TC_178_verifyAirSettingsScreen.feature
Internal Air Setup - AIR Settings - Verify AIR settings sceen, change values and save - Passenger Type | Pass | Yes |  | Kavitha |  |  |  |  | air_SMK_TC160_TC_178_verifyAirSettingsScreen.feature
Internal Air Setup - AIR Settings - Verify AIR settings sceen, change values and save - Ticketing | Pass | Yes |  | Kavitha |  |  |  |  | air_SMK_TC160_TC_178_verifyAirSettingsScreen.feature
Internal Air Setup - AIR Settings - Verify AIR settings sceen, change values and save - Default Fare Type Code | Pass | Yes |  | Kavitha |  |  |  |  | air_SMK_TC160_TC_178_verifyAirSettingsScreen.feature
Internal Air Setup - AIR Settings - Verify AIR settings sceen, change values and save - Booking | Pass | Yes |  | Kavitha |  |  |  |  | air_SMK_TC160_TC_178_verifyAirSettingsScreen.feature
Internal Air Setup - AIR Settings - Verify AIR settings sceen, change values and save - Allotment PNR Name Update | Pass | Yes |  | Kavitha |  |  |  |  | air_SMK_TC160_TC_178_verifyAirSettingsScreen.feature
Internal Air Setup - AIR Settings - Verify AIR settings sceen, change values and save - AIAN Configuration | Pass | Yes |  | Drisya |  |  |  |  | air_SMK_TC160_TC_178_verifyAirSettingsScreen.feature
Internal Air Setup - AIR Settings - Verify AIR settings sceen, change values and save - FP Configuration | Pass | Yes |  | Drisya |  |  |  |  | air_SMK_TC160_TC_178_verifyAirSettingsScreen.feature
Internal Air Setup - AIR Settings - Verify AIR settings sceen, change values and save - Residual Seat Info | Pass | Yes |  | Drisya |  |  |  |  | air_SMK_TC160_TC_178_verifyAirSettingsScreen.feature
Internal Air Setup - AIR Settings - Verify AIR settings sceen, change values and save - Air Cost Optimization | Pass | Yes |  | Drisya |  |  |  |  | air_SMK_TC160_TC_178_verifyAirSettingsScreen.feature
Internal Air Setup - AIR Settings - Verify AIR settings sceen, change values and save - Auto Book Generic Flights | Pass | Yes |  | Drisya |  |  |  |  | air_SMK_TC160_TC_178_verifyAirSettingsScreen.feature
Internal Air Setup - AIR Settings - Verify AIR settings sceen, change values and save - Air Twostep Modification Providers | Pass | Yes |  | Drisya |  |  |  |  | air_SMK_TC160_TC_178_verifyAirSettingsScreen.feature
Internal Air Setup - AIR Settings - Verify AIR settings sceen, change values and save - Air Inventory Hold | Pass | Yes |  | Drisya |  |  |  |  | air_SMK_TC160_TC_178_verifyAirSettingsScreen.feature
Internal Air Setup - AIR Settings - Verify AIR settings sceen, change values and save - Auto Rebook GDS Flights | Pass | Yes |  | Drisya |  |  |  |  | air_SMK_TC160_TC_178_verifyAirSettingsScreen.feature
Internal Air Setup - AIR Settings - Verify AIR settings sceen, change values and save - AutoRelease Unsold Inventory | Pass | Yes |  | Drisya |  |  |  |  | air_SMK_TC160_TC_178_verifyAirSettingsScreen.feature
Internal Air Setup - AIR contract - Edit Cost & Price for an AIR Contract | Pass | No |  | Merin
Internal Air Setup - AIR Fare Rule Description - Create a record in AIR Fare Rule Master | Pass | Yes | [6 empty] | air_SMK_TC180_InternalAirSetupAIRFareRuleCode.feature
Internal Air Setup - AIR Fare Rule Description - Create a record in AIR Fare Rule Description | Pass | Yes | [6 empty] | air_SMK_TC180_InternalAirSetupAIRFareRuleCode.feature
Internal Air Setup - AIR MCT - Create a standard MCT | Pass | Yes | [6 empty] | air_SMK_TC182_CreateListStandardMCT.feature
Agency Listing & Search(Existing) | Pass | Yes |  | Merin |  |  |  |  | AgencyListingAndSearch_NewAndExisting.feature
Agency Listing & Search( New) | Pass | Yes |  | Merin |  |  |  |  | AgencyListingAndSearch_NewAndExisting.feature
Agency Search -View Agency privilege disabled | Pass | No | NA70320agncy | Neethi
Agency Activate & Deactivate (Privilege enabled & disabled) | Pass | No | NA70320agncy | Neethi
Delete Agency (Privilege enabled ) | Pass | Yes | [6 empty] | DeleteAgency.feature
Delete Agency (Privilege disabled ) | Pass | No | NA70320agncy | Neethi
Copy Agency (Privilege enabled & disabled ) | Fail | No |  | Neethi | ITRVL34RCG-49690
Edit Agency (Privilege Enabled & Disabled) | Fail | No |  | Neethi | ITRVL34RCG-49690
Agency Control ->with Edit Privilege enabled for Agency Control-> Add,UPD,View General Info,Accounting Control, Security Deposit Information, Credit Information,Agency Credit Balance Update Rules | Pass | Yes |  | Merin |  |  |  |  | TC01_CreateAgencyControls_General_Info.feature
Agency Control Edit (Privilege Enabled & Disabled) | Fail | No |  | Shine | ITRVL34RCG-49690 | New
Agency Group Search (Existing ) | Pass | Yes | [6 empty] | AgencyGroupSearch_NewAndExisting.feature
Agency Group Search ( New) | Pass | Yes | [6 empty] | AgencyGroupSearch_NewAndExisting.feature
Agency Group Edit (with privilege) | Pass | Yes | [6 empty] | AgencyGroupEditAndView.feature
Agency Group Edit (without Privilege) | Pass | No |  | Neethi
Agency Group Deletion (with privilege) | Pass | Yes |  | Merin |  |  |  |  | DeleteAgencyGroup.feature
Agency Group Deletion (without Privilege) | Pass | No |  | Neethi
Agency Branch Search (Existing ) | Pass | Yes |  | Merin |  |  |  |  | AgencyBranchSearch_NewAndExisting.feature
Agency Branch Search (New) | Pass | Yes |  | Merin |  |  |  |  | AgencyBranchSearch_NewAndExisting.feature
Agency Branch Edit & View(with privilege) | Pass | Yes |  | Merin |  |  |  |  | AddAgencyBranch.feature
Agency Branch Edit(without Privilege) | Pass | No |  | Gracy
Agency Branch Deactivate (with privilege ) | Pass | Yes |  | Merin |  |  |  |  | AddAgencyBranch.feature
Agency Branch Deletion (with privilege ) | Pass | Yes |  | Merin |  |  |  |  | AddAgencyBranch.feature
Agency Branch Deletion (without privilege) | Pass | No |  | Gracy
Agent Creation ->Maintain Agents | Fail | Yes |  | Neethi | ITRVL34RCG-49718 |  |  |  | AddAgent.feature
Agent Edit & View (with privilege ) | Fail | Yes |  | Neethi | ITRVL34RCG-49718 |  |  |  | AddAgent.feature
Agent Edit & View (without Privilege) | Pass | No |  | Kavitha
Agent Deactivate (with privilege ) | Fail | Yes |  | Neethi | ITRVL34RCG-49718 |  |  |  | AddAgent.feature
Agent Delete (with privilege ) | Fail | Yes |  | Neethi | ITRVL34RCG-49718 |  |  |  | AddAgent.feature
Agent Deletion (without Privilege) | Pass | No |  | Kavitha
Agency Definition -Add (General Info, Consortium,Meta Tag) | Fail | Yes |  | Neethi | ITRVL34RCG-49690 |  |  |  | AddAgencyDefinition.feature
Agency Definition --Edit (General Info, Consortium,Meta Tag) | Fail | No |  | Neethi | ITRVL34RCG-49690
Agency Definition - View | Pass | No | QA120 | Neethi
Agency Commission -List Commission-Copy - CRUISE_Standard_Commission(With privilege) | Pass | Yes | CRUCNSTLN25 | Neethi |  |  |  |  | TC2_CopyAgencyCommissionRule.feature | Check for ruleType = 'S' in Scenario Steps
Agency Commission -List Commission-Copy - CRUISE_Bonus_Commission(With privilege) | Pass | Yes | DK_AGENCY_18_COMM_CRU_1401 | Neethi |  |  |  |  | TC2_CopyAgencyCommissionRule.feature | Check for ruleType = 'B' in Scenario Steps
Agency Commission -List Commission-Copy - AIR_Standard_Commission(With privilege) | Pass | Yes | AIRTIERGOLD20 | Neethi |  |  |  |  | TC2_CopyAgencyCommissionRule.feature | Check for ruleType = 'S' in Scenario Steps
[9 empty] | TC2_CopyAgencyCommissionRule.feature | Check for ruleType = 'S' in Scenario Steps
Agency Commission -List Commission-Copy - HTL_Standard_Commission(With privilege) | Pass | No |  | Gracy |  |  |  |  | TC2_CopyAgencyCommissionRule.feature | Check for ruleType = 'B' in Scenario Steps
Agency Commission -List Commission-Copy - PKG_Standard_Commission(With privilege) | Pass | Yes |  | Gracy |  |  |  |  | TC2_CopyAgencyCommissionRule.feature | Check for ruleType = 'S' in Scenario Steps
Agency Commission -List Commission-Copy - PKG_Bonus_Commission(With privilege) | Pass | Yes |  | Gracy |  |  |  |  | TC2_CopyAgencyCommissionRule.feature | Check for ruleType = 'B' in Scenario Steps
Agency Commission -List Commission-Copy - MISC_Standard_Commission(With privilege) | Pass | Yes |  | Gracy |  |  |  |  | TC2_CopyAgencyCommissionRule.feature | Check for ruleType = 'S' in Scenario Steps
Agency Commission -List Commission-Copy - MISC_Bonus_Commission(With privilege) | Pass | Yes |  | Gracy |  |  |  |  | TC2_CopyAgencyCommissionRule.feature | Check for ruleType = 'B' in Scenario Steps
Agency Commission -List Commission-Copy - TRF_Standard_Commission(With privilege) | Pass | Yes |  | Gracy |  |  |  |  | TC2_CopyAgencyCommissionRule.feature | Check for ruleType = 'S' in Scenario Steps
Agency Commission -List Commission-Copy - TRF_Bonus_Commission(With privilege) | Pass | Yes |  | Gracy |  |  |  |  | TC2_CopyAgencyCommissionRule.feature | Check for ruleType = 'B' in Scenario Steps
Agency Commission -List Commission-Activate/Deactivate(With privilege)-CRUISE | Pass | Yes |  | Gracy |  |  |  |  | TC13-ActivateAndDeactivateAgencycommissionRule.feature
Agency Commission -List Commission-Create and Delete(With privilege)-CRUISE_Standard_Commission | Pass | Yes |  | Gracy |  |  |  |  | TC3-CRU-CreateAgencyCommWithAllFields.feature | Check for ruleType = 'S' in Scenario Steps
Agency Commission -List Commission-Create and Delete(With privilege)-CRUISE_Bonus_Commission | Pass | Yes |  | Gracy |  |  |  |  | TC3-CRU-CreateAgencyCommWithAllFields.feature | Check for ruleType = 'B' in Scenario Steps
Agency Commission -List Commission-View, Copy, Activate, Deactivate, Delete (Without privilege) | Pass | No |  | Akshay
Agency Commission -Standard commission- Products(ADD/EDIT) | Pass | Yes | STD_16 | Kavitha |  |  |  |  | TC1_CreateAgencyCommission_mandatoryFields.feature
Agency Commission -Bonus commission- Cruise(ADD/EDIT) | Pass | Yes | BON_16 | Kavitha |  |  |  |  | TC1_CreateAgencyCommission_mandatoryFields.feature
Ship deployment - Search Cruise itinerary(master cruise with sub cruises) in ship deployment screen (search with Ship Code) | Pass | No |  | Gracy
Ship deployment - Add/Delete port of calls(Master and subcruises) with impacting /without impacting subcruises/interporting cruises | Pass | No | KO_16012026_115151 JL_16012026_122006 | Akshay
Ship deployment - Change Ports(Embarkation/Disembarakation/Port of calls) with impacting /without impacting subcruises/interporting cruises | Pass | No | JL_16012026_101514, J2222F, N782A2 | Shine
Ship deployment - Change Date(Embarkation/Disembarakation/Port of calls) with impacting /wiithout impacting subcruises/interporting cruises | Pass | No | JL_16012026_101514, J2222F, N782A2 | Shine
Ship deployment - Change Time(Embarkation) without impacting subcruises/interporting cruises | Pass | Yes | FZ_16012026_095732 | Drisya |  |  |  | ARGO-83222 | TC01_ChangeDepartureTime_WithOrWithoutImpactOnSegmentOrInterportCruise.feature
Ship deployment - Change Time(Disembarakation) without impacting subcruises/interporting cruises | Pass | Yes | FZ_16012026_095732 | Drisya |  |  |  | ARGO-83226 | TC01_ChangeDepartureTime_WithOrWithoutImpactOnSegmentOrInterportCruise.feature
Ship deployment - Change Time(arrival & dept time of Port of calls) without impacting subcruises/interporting cruises | Pass | Yes | DP_16012026_114929 | Akshay |  |  |  | ARGO-83224 | TC01_ChangeDepartureTime_WithOrWithoutImpactOnSegmentOrInterportCruise.feature
Ship deployment - Change Time(Embarkation) with impacting subcruises/interporting cruises | Pass | Yes | JL_16012026_101514, J2222F, N782A2 | Shine |  |  |  | ARGO-83230 | TC01_ChangeDepartureTime_WithOrWithoutImpactOnSegmentOrInterportCruise.feature
Ship deployment - Change Time(Disembarakation) with impacting subcruises/interporting cruises | Pass | Yes | JL_16012026_101514, J2222F, N782A2 | Shine |  |  |  | ARGO-83232 | changeArrivalDepartureTime_WithImpact.feature
Ship deployment - Change Time(arrival & dept time of Port of calls) with impacting subcruises/interporting cruises | Pass | Yes | FZ_16012026_115732 | Akshay |  |  |  | ARGO-83234 | changeArrivalDepartureTime_WithImpact.feature
Master Uploads - RATINGMASTER - ADD | Pass | Yes | [5 empty] | TC_20
Master Uploads - CURRENCYMASTER - ADD | Pass | Yes | [5 empty] | TC_21
Master Uploads - PERSONTYPEMASTER - ADD | Pass | Yes | [5 empty] | TC_22
Master Uploads - STATEMASTER -ADD | Pass | Yes | [5 empty] | TC_23
Master Uploads - CITYMASTER - ADD | Pass | Yes | [5 empty] | TC_24
Master Uploads - REGIONMASTER - ADD | Pass | Yes | [5 empty] | TC_25
Master Uploads - BRANDSMASTER - ADD | Pass | Yes | [5 empty] | TC_26
Master Uploads - COUNTRYMASTER - ADD | Pass | Yes | [5 empty] | TC_27
Master Uploads - PORTMASTER - ADD | Pass | Yes | [5 empty] | TC_28
Master Uploads - RATETYPEMASTER - ADD | Pass | Yes | [5 empty] | TC_29
Master Uploads - TITLEMASTER - ADD | Pass | Yes | [5 empty] | TC_30
Master Uploads - RATECLASSIFICATIONMASTER - ADD | Pass | Yes | [5 empty] | TC_31
Master Uploads - CABINTYPEMASTER - ADD | Pass | Yes | [5 empty] | TC_33
Master Uploads - CRUISEBEDTYPEMASTER - ADD | Pass | Yes | [5 empty] | TC_34
Master Uploads - PORTCLASSIFICATIONSMASTER - ADD | Pass | Yes | [5 empty] | TC_35
Master Uploads - SHIPCLASSMASTER - ADD | Pass | Yes | [5 empty] | TC_36
Master Uploads - TRAININGSMASTER - ADD | Pass | Yes | [5 empty] | TC_37
Master Uploads - NATIONALITYMASTER - ADD | Pass | Yes | [5 empty] | TC_38
Master Uploads - PACKAGECLASSIFICATIONMASTER - ADD | Pass | Yes | [5 empty] | TC_39
Master Uploads - MARKETMASTER - ADD | Pass | Yes | [5 empty] | TC_40
Master Uploads - FLEETMASTER - ADD | Pass | Yes | [5 empty] | TC_41
Master Uploads - GROUPCATEGORYMASTER - ADD | Pass | Yes | [5 empty] | TC_42
Master Uploads - GROUPCLASSIFICATIONMASTER - ADD | Pass | Yes | [5 empty] | TC_43
Master Uploads - CRUISECATEGORYCLASSMASTER - ADD | Pass | Yes | [5 empty] | TC_44
Master Uploads - CRUISELINESMASTER - ADD | Pass | Yes | [5 empty] | TC_45
Master Uploads - CRUISETYPEMASTER - ADD | Pass | Yes | [5 empty] | TC_46
Master Uploads - SHIPFACILITYMASTER - ADD | Pass | Yes | [5 empty] | TC_47
Master Uploads - SHIPLOCATIONMASTER - ADD | Pass | Yes | [5 empty] | TC_48
Master Uploads - LANGUAGEMASTER - ADD | Pass | Yes | [5 empty] | TC_49
Master Uploads - LOYALTYLEVELMASTER - ADD | Pass | Yes | [5 empty] | TC_50
Master Uploads - LOYALTYPROGRAMMASTER - ADD | Pass | Yes | [5 empty] | TC_51
Master Uploads - SURCHARGEGROUPMASTER - ADD | Pass | Yes | [5 empty] | TC_52
Master Uploads - CHARGETYPEMASTER - ADD | Pass | Yes | [5 empty] | TC_53
Master Uploads - AGENCYCLASSMASTER -ADD | Pass | Yes | [5 empty] | TC_54
Master Uploads - AGENCYCONSORTIUMMASTER - ADD | Pass | Yes | [5 empty] | TC_55
AIR_Master Uploads - Airport Masters - ADD | Pass | Yes | [5 empty] | TC_56
AIR_Master Uploads - Airline Masters - ADD | Pass | Yes | [5 empty] | TC_57
AIR_Master Uploads - Air Fare Class Masters - ADD | Pass | Yes | [5 empty] | TC_58
AIR_Master Uploads - Air Cabin Class Masters - ADD | Pass | Yes | [5 empty] | TC_59
Longtail Master Uploads - Miscellaneous Item Master - ADD | Pass | Yes | [5 empty] | TC_60
Longtail Master Uploads - Transfer Prod Type Master - ADD | Pass | Yes | [5 empty] | TC_61
Longtail Master Uploads - Hotel Chain Master - ADD | Pass | Yes | [5 empty] | TC_62
Longtail Master Uploads - Hotel Facility Master - ADD | Pass | Yes | [5 empty] | TC_63
Longtail Master Uploads - Hotel Rating Master - ADD | Pass | Yes | [5 empty] | TC_64
Longtail Master Uploads - Hotel Type Master - ADD | Pass | Yes | [5 empty] | TC_65
Uploads -Ship Set up - Ship Definition - ADD | Pass | Yes | [5 empty] | TC_66
Uploads -Ship Set up - Decks - ADD | Pass | Yes | [5 empty] | TC_67
Uploads -Ship Set up - Ship Configuration - ADD | Pass | Yes | [5 empty] | TC_68
Uploads -Ship Set up - Ship Category Upload - ADD | Pass | Yes | [5 empty] | TC_69
Uploads -Ship Set up - Ship CabinUpload - ADD | Pass | Yes | [5 empty] | TC_70
Uploads -Ship Set up - Muster Station - ADD | Pass | Yes | [5 empty] | TC_71
Uploads -Ship Set up - Ship Definition - UPD | Pass | Yes | [5 empty] | TC_72
Uploads -Ship Set up - Decks - UPD | Pass | Yes | [5 empty] | TC_73
Uploads -Ship Set up - Ship Configuration - UPD | Pass | Yes | [5 empty] | TC_74
Uploads -Ship Set up - Ship Category Upload - UPD | Pass | Yes | [5 empty] | TC_75
Uploads -Ship Set up - Ship CabinUpload - UPD | Pass | Yes | [5 empty] | TC_76
Uploads -Ship Set up - Muster Station - UPD | Pass | Yes | [5 empty] | TC_77
Ship Set up Uploads - Muster Station - Status value -Inactive | Pass | Yes | [5 empty] | TC_78
Ship Set up Uploads - Muster Station - Status value -Blank | Pass | Yes | [5 empty] | TC_79
Uploads -Ship Set up - Muster Station - DEL | Pass | Yes | [5 empty] | TC_80
Uploads -Ship Set up - Ship CabinUpload - DEL | Pass | Yes | [5 empty] | TC_81
Uploads -Ship Set up - Ship Category Upload - DEL | Pass | Yes | [5 empty] | TC_82
Uploads -Ship Set up - Ship Configuration - DEL | Pass | Yes | [5 empty] | TC_83
Uploads -Ship Set up - Decks - DEL | Pass | Yes | [5 empty] | TC_84
Uploads -Ship Set up - Ship Definition - DEL | Pass | Yes | [5 empty] | TC_85
Uploads - Itinerary - ADD | Pass | Yes | [5 empty] | TC_86
Uploads - Itinerary - UPD | Pass | Yes | [5 empty] | TC_87
Uploads - Itinerary - INACTIVE | Pass | Yes | [5 empty] | TC_88
Uploads - Package - Catalogue,Controls,Categories,Itinerary,Cruise Itinerary,Hotel Itinerary,AIR Itinerary,Activity Itinerary ,Misc Itinerary,Transfer Itinerary -ADD | Pass | Yes |  | Greeshma | pack1601 |  |  | TC_89
Uploads - Package - Catalogue,Controls,Categories,Itinerary,Cruise Itinerary,Hotel Itinerary,AIR Itinerary,Activity Itinerary ,Misc Itinerary,Transfer Itinerary -UPD | Pass | Yes |  | Greeshma |  |  |  | TC_90
Uploads of Long Tail Products - Hotel Catalogue - Hotel Definition,Nearby Locations,Contact Person,Hotel Facilities,Hotel Category,Meal Plan,Hotel Wings,Category Facilities,Controls - ADD | Pass | Yes |  | Gracy |  |  |  | TC_91
Uploads of Long Tail Products - Hotel Rate Plan - Hotel General Info, Hotel Applicability Criteria, Hotel Controls and Inclusions, Per Person- ADD | Pass | Yes | SMK324DOMA | Akshay |  |  |  | TC_92
Uploads of Long Tail Products - Hotel Rate Plan - Hotel General Info, Hotel Applicability Criteria, Hotel Controls and Inclusions, Per Room - ADD | Pass | Yes | Ref id : 4385 | Shine |  |  |  | TC_93
Uploads of Long Tail Products - Hotel Rate Plan - Hotel General Info, Hotel Applicability Criteria, Hotel Controls and Inclusions, Per Occupancy - ADD | Pass | Yes | [5 empty] | TC_94
Uploads of Long Tail Products - Hotel Rate Plan - Hotel General Info, Hotel Applicability Criteria, Hotel Controls and Inclusions, Extra Pricing, Meal Pricing - ADD | Pass | Yes | [5 empty] | TC_95
Uploads of Long Tail Products - Hotel Inventory - Free Pool - ADD | Pass | Yes | Ref id : 4411 | Shine |  |  |  | TC_96
Uploads of Long Tail Products - Miscellaneous Catalogue - Miscellaneous Definition,Contact Person, Categories, Service Location, Controls - ADD | Pass | Yes | [5 empty] | TC_97
Uploads of Long Tail Products - Miscellaneous Inventory - Miscellaneous Inventory, Cutback and Release - ADD | Pass | Yes
Uploads of Long Tail Products - Transfer Catalogue - Definitions - Operating times,Vehicle Type, Definitions, Facilities, Contat Person, ControlsContact Person - ADD | Pass | Yes | TRF_SM32 | Akshay |  |  |  | TC_99
Uploads of Long Tail Products - Transfer Rate Plan - Transfer General Info,Transfer Controls Inclusions,Transfer Applicability Criteria - ADD | Pass | Yes | [5 empty] | TC_100
Uploads of Long Tail Products - Transfer Rate Plan - Transfer General Info,Transfer Controls Inclusions,Transfer Applicability Criteria,Per Person - ADD | Pass | Yes | [5 empty] | TC_101
Uploads of Long Tail Products - Transfer Rate Plan - Transfer General Info,Transfer Controls Inclusions,Transfer Applicability Criteria,Per Unit - ADD | Pass | Yes | RP_TRF1014 | Akshay |  |  |  | TC_102
Uploads of Long Tail Products - Transfer Rate Plan - Transfer General Info,Transfer Controls Inclusions,Transfer Applicability Criteria,Mixed - ADD | Pass | Yes | smk327msit1 | Akshay |  |  |  | TC_103
Uploads of Long Tail Products - Transfer Route - Manage Route,Segment,Pick Up,Drop Off - ADD | Pass | Yes | [5 empty] | TC_104
Uploads - Cruise Rateplan Definition - ADD - PER PERSON | Pass | Yes | RP_326_PP | Akshay |  |  |  | TC_105
Uploads - Cruise Rateplan Definition - ADD - OCCUPANCY | Pass | Yes | Ref id : 4383 | Shine |  |  |  | TC_106
Uploads - Cruise Rateplan Definition - DEL - PER PERSON | Pass | Yes | RP_326_PP | Akshay |  |  |  | TC_107
Uploads - Cruise Rateplan Definition - DEL - OCCUPANCY | Pass | Yes | Ref id : 4384 | Shine |  |  |  | TC_108
Uploads - Cruise Catalogue - ADD | Pass | Yes | Ref id : 4377 | Shine |  |  |  | TC_109
Uploads - Cruise Catalogue - UPD | Pass | Yes | Ref id : 4378 | Shine |  |  |  | TC_110
Ship Set up - Ship Definition -Template Download status verification | Pass | Yes | [5 empty] | TC_111
Ship Set up - Decks -Template Download status verification | Pass | Yes | [5 empty] | TC_112
Ship Set up - Ship Configuration -Template Download status verification | Pass | Yes | [5 empty] | TC_113
Ship Set up - Ship Category -Template Download status verification | Pass | Yes | [5 empty] | TC_114
Ship Set up - Ship CabinUpload -Template Download status verification | Pass | Yes | [5 empty] | TC_115
Ship Set up - Muster Station -Template Download status verification | Pass | Yes | [5 empty] | TC_116
Itinerary Upload - Itinerary Upload -Template Download status verification | Pass | Yes | [5 empty] | TC_117
Cruise Upload - Rateplan Definition, Cabin Rate -Template Download status verification | Pass | Yes | [5 empty] | TC_118
Cruise Upload - Cruise Catalogue -Template Download status verification | Pass | Yes | [5 empty] | TC_119
Package - Catalogue,Controls,Categories,Itinerary,Cruise Itinerary ,Hotel Itinerary ,AIR Itinerary,Activity Itinerary ,Misc Itinerary, Transfer Itinerary -Template Download status verification | Pass | Yes | [5 empty] | TC_120
Long Tail Products - Hotel Definition - Hotel Catalogue -Template Download status verification | Pass | Yes | [5 empty] | TC_121
Long Tail Products - Hotel Rate Plan Upload- Extra Pricing,Meal Pricing, Genaral Info, Hotl Applicability Criteria,Controls and Inclusions,Per Room,Per Occupancy,Per Person -Template Download status verification | Pass | Yes | [5 empty] | TC_122
Long Tail Products - Hotel Inventory Upload-Free Pool-Template Download status verification | Pass | Yes | [5 empty] | TC_123
Long Tail Products - Miscellaneous Catalogue - Miscellaneous Definition,Contact Person,CategoriesService Location,Controls -Template Download status verification | Pass | Yes | [5 empty] | TC_124
Long Tail Products - Miscellaneous Inventory - Miscellaneous Inventory -Template Download status verification | Pass | Yes | [5 empty] | TC_125
Long Tail Products - Transfer Catalogue - Definitions - Operating times,Vehicle Type, Definitions, Facilities, Contat Person, ControlsContact Person -Template Download status verification | Pass | Yes | [5 empty] | TC_126
Long Tail Products - Transfer Rate Plan - Transfer_General_info,Transfer_Controls_Inclusions,Transfer_Applicability_CriteriaPer_Person ,Per_Unit,Mixed -Template Download status verification | Pass | Yes | [5 empty] | TC_127
Long Tail Products - Transfer Route - Manage Route,Segment ,Pick Up,Drop Off-Template Download status verification | Pass | Yes | [5 empty] | TC_128
Master - STATEMASTER -Template Download status verification | Pass | Yes | [5 empty] | TC_129
Master - PERSONTYPEMASTER - Template Download status verification | Pass | Yes | GTP | Akshay |  |  |  | TC_130
Master - CITYMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_131
Master - REGIONMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_132
Master - BRANDSMASTER - Template Download status verification | Pass | Yes | SMK327 | Akshay |  |  |  | TC_133
Master - COUNTRYMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_134
Master - PORTMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_135
Master - RATETYPEMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_136
Master - TITLEMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_137
Master - RATECLASSIFICATIONMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_138
Master - RATINGMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_140
Master - CABINTYPEMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_141
Master - CRUISEBEDTYPEMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_142
Master - PORTCLASSIFICATIONSMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_143
Master - SHIPCLASSMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_144
Master - TRAININGSMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_145
Master - NATIONALITYMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_146
Master - PACKAGECLASSIFICATIONMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_147
Master - CURRENCYMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_148
Master - MARKETMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_149
Master - FLEETMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_150
Master - GROUPCATEGORYMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_151
Master - GROUPCLASSIFICATIONMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_152
Master - CRUISECATEGORYCLASSMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_153
Master - CRUISELINESMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_154
Master - CRUISETYPEMASTER - Template Download status verification | Pass | Yes | [5 empty] | TC_155
Master - SHIPFACILITYMASTER - Template Download status verification | Pass | Yes
Master - SHIPLOCATIONMASTER - Template Download status verification | Pass | Yes
Master - LANGUAGEMASTER - Template Download status verification | Pass | Yes
Master - LOYALTYLEVELMASTER - Template Download status verification | Pass | Yes
Master - LOYALTYPROGRAMMASTER - Template Download status verification | Pass | Yes
Master - SURCHARGEGROUPMASTER - Template Download status verification | Pass | Yes
Master - CHARGETYPEMASTER - Template Download status verification | Pass | Yes | SMK | Akshay
Master - AGENCYCLASSMASTER -Template Download status verification | Pass | Yes
Master - AGENCYCONSORTIUMMASTER - Template Download status verification | Pass | Yes
Longtail Master - Hotel Chain Master - Template Download status verification | Pass | Yes
Longtail Master - Hotel Facility Master - Template Download status verification | Pass | Yes
Longtail Master - Hotel Rating Master - Template Download status verification | Pass | Yes
Longtail Master - Hotel Type Master - Template Download status verification | Pass | Yes
Longtail Master - Transfer Prod Type Master - Template Download status verification | Pass | Yes
Longtail Master - Miscellaneous Item Master - Template Download status verification | Pass | Yes
AIR_Master - Airport Masters - Template Download status verification | Pass | Yes
AIR_Master - Airline Masters - Template Download status verification | Pass | Yes
AIR_Master - Air Cabin Class Masters - Template Download status verification | Pass | Yes
AIR_Master - Air Fare Class Masters - Template Download status verification | Pass | Yes
Cruise Booking- Create a single cabin real booking | Pass | Yes | [6 empty] | createSingleCabinBkg.feature
Cruise Booking- Create a multi cabin real booking | Pass | Yes | [6 empty] | multiCabinRealBooking.feature
Cruise Booking- Create a Guarantee booking (Single) | Pass | Yes | [6 empty] | createGuaranteeBkg.feature
Cruise Booking- Create a Guarantee booking (Multi) | Pass | Yes | A2AG73 | Kavitha |  |  |  |  | ARGO-88741_GTYBooking_multiCabin_multiPax.feature
Cruise Booking- Create a Waitlist booking (Single) | Pass | Yes | [6 empty] | CreateWaitListBooking_Single.feature
Cruise Booking- Create a Waitlist booking (Multi) | Pass | Yes | [6 empty] | ARGO-88660_WLBkng_multiCabin_multiPax.feature
Single/Multi Real Cabin Booking with WL preference ( selection from category listing screen) | Pass | Yes | [6 empty] | ARGO-90401_WLPreferenceBkng_SettingsEnabled.featureFeature: ARGO-90401 - Waitlist Preference Control_Do a waitlist preference booking - Settings enabled,privilege enabled
Add attachments to a booking from Booking Conf Screen | Fail | No |  | Greeshma | ITRVL34RCG-49667 | New
Add attachments against a passenger (Pax doc attachments) in Create Booking | Fail | No |  | Kavitha | ITRVL34RCG-47190 | Existing
View Attached documents after retrieving a booking | Fail | No |  | Neethi | ITRVL34RCG-49667
Agency Commission - Restriction & Booking Level Commission and Verify in Selling | Blocked | No |  | Akshay | ITRVL34RCG-49681 | New
Create a package with Cruise,Misc and hotel and check availability in shopping | Pass | No | Fz-cruise3 , pack3 | Greeshma
Create a package booking including Cruise,Misc and Hotel | Pass | No | G2AAB9 | Greeshma
Review Cart Package-View Package Details | Pass | No | G2AAB9 | Greeshma
Cruise Shopping with Different payment method (Cash,Bankwire,Cheque) | Pass | No | H6222F | Greeshma
Package Shopping with Different payment method (Cash,Bankwire,Cheque) | Pass | No | G2AAB9 | Greeshma
Revalidate Cart Manual - Notify of Gross Price Change or If item becomes Unavailable (Cruise/Package) | Pass | No |  | Drisya
Revalidate Cart Automatic -: Notify of Gross Price Change or If item becomes Unavailable(Cruise/Package) | Pass | No |  | Drisya
Revalidate Cart Manual - Cruise alone | Pass | No | cart - 52653 | Greeshma
Revalidate from pax info screen -: Pax type changes and price changes (Cruise/Package) | Pass | No |  | Drisya
Cruise Shopping-Search & Listing-Advance Search(except search by cabin attributes) | Pass | No |  | Drisya
Cruise Shopping-Search & Listing ,based on various availablity and applicability | Pass | No |  | Drisya
Cruise Search & Listing -Details-Departures | Pass | No |  | Drisya
Cruise Search & Listing -Details-Calendar View | Pass | No |  | Neethi
Cruise Search & Listing -Details-Show available and Past cruises | Pass | No |  | Drisya
UI: Ship setup(ship,deck,cabin configuration,category,cabin)- ADD/EDIT | Pass | No | JL | Neethi
UI: Ship setup(ship,deck,cabin configuration,category,cabin)- DEL | Pass | No | LJ | Neethi
UI: Cruise setup ,itinerary definition, shopping listing and booking | Pass | No | ITIN_16, SD050126004, H7222F | Kavitha
Add/Copy/Edit/Delete Facilities & Bed Config | Pass | No |  | Kavitha
Cruise propagation from Cruise catelogue page | Pass | No | SD050626004 | Kavitha
Deck Plan Setup | Fail | No |  | Akshay | ITRVL34RCG-49686 | New
Booking Contact - B2E Booking flow | Pass | No |  | Kavitha
Booking Contact Details in Cart & Booking | Pass | No |  | Merin | BM5222
Setup Internal AIR and check whether available in shopping (One Way/Two way/Multicity) | Pass | No | AAHD22 | Kavitha
Booking flow - Air- One way | Pass | No | AAHD22 | Kavitha
Booking flow - Air- Two way | Pass | No |  | Merin
Booking flow - Air- Multi City | Pass | No | X22285 | Shine
AIR Excel Upload-Flight Definition & Inventory | Pass | No | JY-1238 | Kavitha
AIR Excel Upload-Air Catalogue | Pass | No | 4410 | Merin
AIR Excel Upload-Air Contract -Cost & Price | Pass | No |  | Merin
AIR Excel Upload-Air Contract -Route | Pass | No | GR3 | Greeshma
Booking Rules -Create service fee Booking Rules, Activate & validate in selling App(Amount/Percentage) | Pass | No | A2J622 | Gracy
Configure workflow code and add item to workflow & complete the task in workflow Dashboard | Pass | No | 210083, A2J562 | Shine
Access Right Retrieval Cart | Pass | No |  | Shine
Access Right Retrieval Booking | Pass | No |  | Merin
Retrieve /Search Cart | Pass | No | 52697 | Neethi
Retrieve /Search Booking | Pass | No | AHJ2AA | Neethi
Mini Cart & Cart-Details-Itinerary,Price , Facilities,Info-Notes & Alerts(Category Listing,Cabin Listing, Cart) | Pass | No |  | Gracy
Change Cabin( with Change cabin in cart privilege enabled)-with Modify Cart already enabled(only for Cart ) | Pass | No | 52719 | Neethi
Add Facility(Only for Cart) | Pass | No |  | Merin | BM5222
Mini Cart & Cart -Add additional Cruise product to a cart with existing cruise ( only for Cart ) | Pass | No | H6222F | Greeshma
Single/Multi Cabin Booking-Auto Assign | Pass | No | Single cabin -A2AG75 multiple cabin -J2AAB9 | Neethi
Shopping Cart Expiry-Configure Cart expiry parameter and validate in Selling App | Pass | No |  | Shine
Category Listing/Cabin Listing -Deck Plan -Show view & Selection for RCG Deck plan | Blocked | No |  | Akshay | ITRVL34RCG-49686 | New
Category Listing/Cabin Listing -Details-Auto Assign widget view | Pass | No |  | Gracy
View/Copy/Edit/Delete Rate Set Definition(with & without Privilege) | Pass | No |  | Gracy
Add Rate Set Definition | Pass | No | RS_327 , RP_OC_327JL , RP_OC_327JL000016469 | Akshay
Add/Edit/Delete Rate Plan Inventory -Both Per person & Per Occupancy | Pass | No |  | Gracy
Search& Filter Rate Plan Inventory Listing | Pass | No |  | Gracy
Copy/Edit Rate Plan Definition (with & without Privilege)- Both Per person & Per Occupancy | Pass | No | SHN70327PPRPCPY, SHN70327OCRPCPY | Shine
Search & Filter Rate Plan Listing-Activate,Deactivate & Delete | Pass | No |  | Greeshma
Add/Delete/Edit/Copy Rate Plan Type Definition (with & without Privilege) | Pass | No |  | Neethi
Search and Filter Rate Plan Type Listing | Pass | No | LAM | Neethi
Search and Filter Rate Set Listing-Activate,Deactivate and Delete | Pass | No | Shn70322RScpy4_1 | Neethi
View Rate Plan- Quick view& Detailed View | Pass | No | 102_SUSRP | Neethi
Create a Discount Promotions and apply in Cruise Booking (Single &Multi Cabin) | Pass | No | smk327cruise , J3222F | Akshay
Create a category upgrade Promotion and apply in Cruise Booking (Single &Multi Cabin) | Fail | No |  | Merin
Cruise Promotions-Discounts & Credits -Fancy Rounding | Pass | No | fancysit1doma , | Akshay
Create Restricted Promotions and apply in booking | Fail | No |  | Merin | ITRVL34-215518
Create a MISC Booking | Pass | Yes
Cart/Passenger/Item Level Remarks( Cart & Booking) | Pass | No | Cart -52719 , Booking - AAAA8Y | Neethi
Remarks Set up | Pass | No | R_70327 | Neethi
Booking History | Pass | No |  | Gracy
TimeLimits-Item Level | Pass | No | A2J562 | Shine
TimeLimits-Booking Level | Pass | No |  | Merin
CAB Freeze & Unfreeze | Pass | No |  | Shine
CAB Dupe Check | Pass | No | RAA229 , H6222F | Greeshma
Cruise -Basic Set up Pricing-Surcharge Cruise domain -Set up | Pass | No | SCH_16 | Kavitha
CAB-Override(Cost, Price,Discount, Add Charge) | Pass | No |  | Merin
Overrides -Payments & Refund in booking | Pass | No |  | Merin
Inventory-Block Inventory | Pass | No | BLK16 | Kavitha
Inventory-Cabin Inventory | Pass | No | A55H22 | Akshay
Inventory-Category Lock | Pass | No | JL030126003 | Akshay
Inventory-Cabin Hold | Pass | No | JL030126003 | Akshay
Inventory-Specific Cut Back and Release | Pass | No | CBR_16012026_071743 CBR_16012026_071810 | Greeshma
Cruise Inventory Search and Listing | Pass | No | KS011926004 | Neethi
Inventory-Guarantee Set Up and do a Guarantee Booking | Pass | No | A2AG73 | Kavitha
Inventory-wailist Set Up and do a waitlist Booking | Pass | No | Q7AAAB | Kavitha
Inventory-Allocated Block Set Up and do a real inventory booking | Pass | No | Q8AAAB. DKDISCITEMPROMO1601 | Drisya
Per Occupancy-Cabin Rate Definition | Pass | No | SHN70327RPOC000016369 | Shine
Group Booking - Group Catalogue Search | Pass | No | Dev_GRP | Akshay
Group Booking - Group Listing Screen | Pass | No |  | Greeshma
Group Booking - Group Program Listing | Pass | No |  | Greeshma
Group Booking - Group category Listing- Allocated with Price protection | Pass | No | AB4L22 | Greeshma
Group Booking - Group category Listing-Non Allocated without Price protection | Pass | No | AA2AJR | Greeshma
Group Booking- Review Cart and create a group Booking | Pass | No | AB4L22 | Greeshma
AIR-Pax Amendments - Name Change,Pax Type change, Split pax,One Click Pax removal | Fail | No |  | Shine | ITRVL34RCG-40552 | Existing
AIR-Cabin Upgrade/Downgrade | Pass | No | Z22285, N742A2 | Shine
AIR-Segment Amendment-Change,Delete | Pass | No | A2J592 | Akshay
AIR-Cancel Booking and cancellation policy | Fail | No |  | Akshay | ITRVL34RCG-47923 | Existing
AIR-OD amendment,Add change delete | Pass | No |  | Merin
Package Shopping & Booking-Cruise Category-Details(Info,Policy,Notes &Alerts,Special Request,Facilities,Price Details) | Pass | Yes
Transfer Shopping &Booking and Inventory Check | Fail | No |  | Merin
Misc Cancel-Cancel Item & Inventory check | Pass | No | A2228 | Merin
Misc Cancel-Cancellation Policy | Pass | No | N792A2 | Neethi
Misc Cancel-Cancel Booking with B2E Flow | Pass | Yes
Agency Shopping & Booking with agency deferred payment | Pass | No | Y22285 | Shine
Package -Journey Planner-View All Items(Mandatory,Excludable,Optional AddOns) | Pass | No |  | Drisya
Package-Journey Planner-View All items(Shuffle &Customize item) | Pass | No |  | Drisya
ARGO-133516-Add a new Vehicle Type(Transfer) | Pass | No | VT_16 | Kavitha
ARGO-133540-Add a new Transfer Route (One way/Round Trip) | Pass | No | RT_1, RT_2 | Kavitha
ARGO-133670-Add Transfer Controls | Pass | No |  | Gracy
ARGO-129337-Download Agency Definition Excel | Pass | No |  | Gracy
ARGO-129347-Upload Agency Definition Excel and validate in UI(ADD action) | Pass | No |  | Gracy
ARGO-129359-Update existing agency Record via excel upload(UPD Action) | Pass | No |  | Gracy
ARGO-129605-Add Per person Cabin Rates | Pass | No |  | Gracy
ARGO-129235-Add Per person Rate Plan | Pass | No | RP_327_PPJL000016449 , RP_327_PPJL | Akshay
Cruise Ancillary set up | Pass | No | FZCRUISE_ANC_1601 | Drisya
ARGO-121242-Ancillary misc shopping and booking | Pass | No | AA2KP2 | Drisya
Ancillary Misc amendment | Pass | No | Q8AAAB | Drisya
ARGO-123292-Create a transfer promotion and booking | Fail | No |  | Shine | ITRVL34RCG-49059 | Existing
ARGO-122653-Group Booking - Create a Cruise promotion and do FIT booking | Pass | No | AB4L22 | Greeshma
Group Booking - Create a Cruise promotion and do agency booking | Pass | No | promogroup327, A2AG76 | Akshay
ARGO-130477-Add Surcharge & Tax for Cruise and verify in selling | Pass | No | Shn70327sur, Shn70327T, A2J562 | Shine
ARGO-130642-Add Surcharge & Tax for Air and verify in selling | Fail | No | Shn70327AirSur, Shn70327AiT | Shine | ITRVL34RCG-47239 | Existing
Copy Ship | Pass | No | TO | Neethi
ARGO-127576-Create a Package promotion with Cruise Product in Applicability- Shop and Create a Booking with the Promotion | Pass | No |  | Gracy | L2AAB9
ARGO-129195-Yield Adjustment | Pass | No | H8222F | Drisya
ARGO-127310-Package Amendment-Amend the booking via Revise Item/Journey Planner - Verify Rule gets applied | Pass | No | H8222F | Drisya
Package Cancellation | Pass | No | PKG_16, H2AAB9 | Kavitha
Transfer Amendments | Fail | No |  | Merin
Transfer Cancellation | Fail | No |  | Merin
Create a Credit Template with Grant Based on Price and Redeem Type Discount - Grant Credit - Redeem in Booking | Pass | No | J4222F | Akshay
Create a Credit Template with Grant Based on Penalty and Redeem Type Discount - Grant Credit - Redeem in Booking | Pass | No | DKPENALTY1601. Granted S222222229 from H8222F. Redeemed in H8222F | Drisya
Create a Credit Template with Grant Based on Refund and Redeem Type Discount - Grant Credit - Redeem in Booking | Pass | No |  | Merin
Create a Credit Template with Grant Based on User input and Redeem Type Discount - Grant Credit - Redeem in Booking | Pass | No | UI16, N762A2 | Kavitha
Create a Credit Template with Grant Based on Price and Redeem Type FOP - Grant Credit - Redeem in Booking | Pass | No | STGFOP3, A2J622 | Gracy
Create a Credit Template with Grant Based on Penalty and Redeem Type FOP - Grant Credit - Redeem in Booking | Pass | No | AA2AJR | Greeshma
Create a Credit Template with Grant Based on Refund and Redeem Type FOP- Grant Credit - Redeem in Booking | Pass | No | REF16, N762A2 | Kavitha
Create a Credit Template with Grant Based on User input and Redeem Type FOP- Grant Credit - Redeem in Booking | Pass | No |  | Merin
Create a Credit Template with Credit Action Upon Cxl = Recredit - Grant Credit - Redeem in Booking - Cxl Booking | Pass | No | Shn70325cred, C22286 | Shine
Create a Credit Template with Credit Action Upon Cxl = NewCredit - Grant Credit - Redeem in Booking - Cxl Booking | Pass | No | K2AAB9 , smk327credit | Akshay
Create a Credit Template with Allow Unredeem = Yes - Grant Credit - Redeem in Booking - Unredeem | Pass | No | DKPENALTY1601. Granted S222222229 from H8222F. Redeemed in H8222F. Unredeemed the same | Drisya
Create a Credit Template with Redeem Multiple Times = Yes - Grant Credit - Redeem Multiple Times in a Booking | Pass | No | EAA232 | Greeshma
Create a Credit Template with Transferability = Yes - Grant Credit - Transfer to another profile | Pass | No | Shn70325cred | Shine
Create a Credit Template with Refundability = Yes - Grant Credit Based on Refund - Refund Credits | Pass | No |  | Gracy
Credit Template - Searching and Listing | Pass | Yes | Credit98 | Neethi
Credit Template - View,Copy,Edit,Activate,Deactivate and Delete (with privilege) | Pass | No | Credit99 | Neethi
Create a Discounted Different Item Promotion and Apply in Booking | Pass | No | Q8AAAB. DKDISCITEMPROMO1601 | Drisya
Create a Free Different Item Promotion and Apply in Booking | Fail | No |  | Merin
Cruise Amendment - Pax Amendmet and Category/Cabin Change. Amendment Fee | Fail | No |  | Akshay | ITRVL34RCG-49707 | New
Cruise Cancellation. Cancellation Fee | Pass | No | A55J22 , SMKCXL320 | Akshay
Group Booking Amendment | Pass | No | AB4L22 | Greeshma
Group Bookign Cancellation | Pass | No | AB4L22 | Greeshma
Create a new Transfer and list in selling | Fail | No |  | Merin
Create an inventoried misc and do a booking | Pass | No | N792A2 | Neethi
Create an non inventoried misc and do a booking | Pass | No | A2228 | Merin
Misc Booking Amendment. Amendment Fee | Pass | No | A2228 | Kavitha
Misc Bookign Cancellation. Cancellation Fee | Pass | No | CXL_16, A2AG74 | Kavitha
Create a New Hotel and list in selling | Pass | No | Q9AAAB | Gracy
Hotel Booking Cancellation. Cancellation Fee | Pass | No | Q9AAAB | Gracy
Verify the Workflow Listing Field"Check Out Date " are Configured Correctly | Pass | No | N752A2, 210138, 333 | Akshay
Verify the Workflow Listing Field"Check Out Date " showing on workflow task details screen | Pass | No | N752A2, 210138, 333 | Akshay
Verify the Workflow Listing Field"Room Category" are Configured Correctly | Pass | No | N752A2, 210138, 333 | Shine
Verify the Workflow Listing Field"Room Category" showing on workflow task details screen | Pass | No | N752A2, 210138, 333 | Shine
Verify the schedule change on FIT Air in which schedule checks failed and do a re run | Fail | No |  | Shine | ITRVL34RCG-49683 | New
Verify the schedule change on FIT Air in which schedule checks failed and do a re run | Fail | No |  | Shine | ITRVL34RCG-49683 | New
Verify user is able to apply surcharge for FIT Air with Rate Model = 'Cost and Price' and Cost basis is Amount and MarkupType is Percentage | Fail | No |  | Shine | ITRVL34RCG-47239 | Existing
Create a surcharge for Air with zero price and verify it is not visible in booking/shopping | Fail | No |  | Shine | ITRVL34RCG-47239 | Existing
Verify the mandatory fields set in configuration screen is actually displayed as mandatory in Surcharge definition screen (Configuration screen is saved for Product Air and mandatory fields set is supplier) | Pass | No |  | Drisya
Verify if user select value for Air route code in Product applicability Air in surcharge definition, then Origin, origin type, destination, destination type fields are disabled | Pass | No |  | Drisya
Create Cruise from List Cruise catalogue screen by enabling Auto generate Cruise ID Setting (Ship Code + Departure Date (MMDDYY) + Voyage Days (3 digits) | Pass | No | SD050126004 | Kavitha
Create Cruise from List Cruise catalogue screen by disabling Auto generate Cruise ID Setting | Pass | No |  | Kavitha
Propagate cruise by enabling Auto generate Cruise ID Setting (Ship Code + Departure Date (MMDDYY) + Voyage Days (3 digits) | Pass | No | SD050626004 | Kavitha
Create Cruise through excel upload by enabling Auto generate Cruise ID Setting (Ship Code + Departure Date (MMDDYY) + Voyage Days (3 digits) | Pass | No | 4405. FZ070226005. | Drisya
Create Cruise through ship deployment screen enabling Auto generate Cruise ID Setting (Ship Code + Departure Date (MMDDYY) + Voyage Days (3 digits) | Pass | No |  | Drisya
Configure only Role in "Access for Manual Credit granting" section in the template and verify user logged in with same Role can view and grant credit | Pass | No |  | Merin
Configure only Users(Include) in "Access for Manual Credit granting" section in the template and loggin as same user and verify user can view and grant credit | Pass | No |  | Merin
Configure Role and Users (Exclude) in "Access for Manual Credit granting" section in the template and login with the user having matching role and user added in Users (Exclude) and verify user cannot view and grant the credit | Pass | No |  | Gracy
Verify user is able to create booking for flexible package with cruise as Lead item for an Allocated Agency Group | Pass | No | A2AG78 | Gracy
Verify user is able to create booking for flexible package with cruise as Lead item for a non Allocated Agency Group | Pass | No | A2AG77 | Akshay
Verify user is able to create on option booking for flexible package with cruise as Lead item for a non Allocated Direct Group | Pass | No | HTA2A2 | Greeshma
Verify user is able to create booking for flexible package with cruise as Lead item for an Allocated Direct Group for 2A1C1I | Pass | No | EAA232 | Greeshma
Verify the details for newly created booking in booking financial enquiry screen | Pass | No | AAAA8Y | Neethi
Verify user is able to create receipt to one or more bookings in Create Customer Receipt Screen and verify in customer transaction list and booking summary screen | Pass | No | R6640S R6641S R6644S | Akshay
Verify user is able to create receipt to one or more bookings in Manage Bulk Receipt Screen | Pass | No | Customer : FIT : Cash :1768555718662 Agency : FIT : CQ : 1768556973310 | Drisya
Verify user is able to Upload bulk receipt to an agency in Upload Bulk Receipt Screen | Fail | No |  | Merin
Verify that user is able to initiate and complete the refund from bulk refund process screen | Pass | No | A2J622 | Gracy
Verify the refunds for booking details in payment& refund pop up screen when user initiate refund from the selling screen | Pass | No |  | Gracy
Verify payment transaction type should be created in customer transaction list screen when user initiate refund from the selling screen | Pass | No | G2AAB9 | Greeshma
Verify transaction types in the customer transaction list screen when user initiate refund from the selling screen(existing credit note should be cancel and new credit note should be created with open status) | Pass | No | G2AAB9 | Greeshma
Complete Funds transfer(from one booking to another booking- one/multiple) and verofy the txn type for source(fund transfer) and destination(receipt) bookings | Pass | No | A55F22, A55G22 | Kavitha
Verify that user able to initiate void for the receipt from the customer receipt details screen and void transaction type should be created in the customer transaction list screen | Pass | No |  | Merin
Verify the invoice in customer transaction list screen When booking amount changes(adding promotion,remove promotion,adding passenger,remove passenger,increase or decrease commission, booking is cancelled) | Pass | No | AA2KP2 | Drisya
Verify two credit notes should be created in the customer transaction list screen for an overpaid agency booking(one is overpayment and one is for commission) | Fail | No |  | Shine | ITRVL34RCG-49681 | New
Verify that user able to initiate commission refund from the bulk refund process screen | Fail | No | Batch Reference 1768560034017, Batch Reference 1768560055394, Batch Reference 1768560076777 | Shine | ITRVL34RCG-49358 | Existing

## Gap Scenarios
Environment : Stage
Version : 7.0.
Date : 16-10-2025
Gaps ID | Smoke Scenarios | Precondition | Test Steps | Squad | Expected result
ARGO-83660 | Verify the Workflow Listing Field"Check Out Date " are Configured Correctly | Hotel Workflow Queue exists in the system. | 1.Log in to iTravel as a Service Request user. 2.Navigate to Business Management > Workflows and Queus > Configure a workflow 3.At the List screen choose status as Pre- Configured & search 4.Click Configure against a workflow 5. Select from "Business Entity" as "RCG hotel Workflow" 6. Click on "Attributes" field. 7. View the data listed in dropdown menu. 8. Select Room Category | Engines | The Workflow Field Name "Check Out Date " should be correctly populated within Attributes Field.
ARGO-83660 | Verify the Workflow Listing Field"Check Out Date " showing on workflow task details screen | Hotel Workflow Queue with attribute value"Check Out Date "exists in the system. | 1. Navigate to selling App 2. retrive and hotel booking that contain checkout date 3.create service request for that 4.navigate to workflow dashboard and check the booking ID | Engines | The added task should show the details for the attribute "Check Out Date "
ARGO-83660 | Verify the Workflow Listing Field"Room Category" are Configured Correctly | Hotel Workflow Queue exists in the system. | 1.Log in to iTravel as a Service Request user. 2.Navigate to Business Management > Workflows and Queus > Configure a workflow 3.At the List screen choose status as Pre- Configured & search 4.Click Configure against a workflow 5. Select from "Business Entity" as "RCG hotel Workflow" 6. Click on "Attributes" field. 7. View the data listed in dropdown menu. 8. Select Room Category | Engines | The Workflow Field Name "Room Category" should be correctly populated within Attributes Field.
ARGO-83660 | Verify the Workflow Listing Field"Room Category" showing on workflow task details screen | Hotel Workflow Queue with attribute value"Room Category "exists in the system. | 1. Navigate to selling App 2. retrive and hotel booking that contain Room category 3.create service request for that 4.navigate to workflow dashboard and check thet ask | Engines | The added task should show the details for the attribute "Room Category"
|  | 1.Navigate to Air->flight timing configuration-> Set a configuration for a Airport | 1.Go to the production | AIR | 1.Flight Definition screen_Pop up displayed in flight definition screen when occurs any cancellation of flight on particular day
|  | 2.Navigate to the settings->organisation settings->Air->booking->Set the time change limit, minimum connection time ,Maximum connection time,User acceptance as YES | 2.Air ->Negotiated Inventory |  | 2.Flight Operation screen_Check the Cancelled date bookings are retieved correctly and could do the schedule change. and get alternative flight confirm message.
|  | 3. Should have a booking Air + cruise booking along with hotel if required. | 3.Search the for the flight |  | 3.Tour OPs Screen_Check the schedule changed status.
|  |  | 4.Change the schedule date in such way that it will cancel the flight on a particular day. |  | 4.Retrieve PNR_ check the details whether the schedule changed or not
5.Save the flight definition.
6.Go to Air-> Flight operation
7.Retrieve the cancelled Air and proceed to alternate fly date .
8.Click on confirm .
9.From Home click on Tour ops
10.click on ops request button.
11.Select the request type as schedule_change and click on search.
12.Click on view history link
13.click on the plus icon with PNR
14.click the PNR link.
15.check the details
16.Retrieve the PNR
| Verify the schedule change on a FIT booking in which the checks are failed. | 1.Navigate to Air->flight timing configuration-> Set a configuration for a Airport | 1.Go to the production | AIR | 1.Flight Definition screen_Pop up displayed in flight definition screen when occurs any cancellation of flight on particular day
|  | 2.Navigate to the settings->organisation settings->Air->booking->Set the time change limit, minimum connection time ,Maximum connection time in such a way that it will fails the schedule checks and select the User acceptance as YES | 2.Air ->Negotiated Inventory |  | 2.Flight Operation screen_Check the Cancelled date bookings are retieved correctly and could do the schedule change. and get alternative flight confirm message.
|  | 3. Should have a booking Air + cruise booking along with hotel if required. | 3.Search the for the flight |  | 3.Tour OPs Screen_Check the schedule changed status.
|  |  | 4.Change the schedule date in such way that it will cancel the flight on a particular day . |  | 4.Retrieve PNR_ check the details whether the schedule changed or not .
|  |  | 5.Save the flight definition. |  | 5.Service Request_Check the failed cases are available in service request
|  |  | 6.Go to Air-> Flight operation |  | 6.Hide flag_Check if hide is yes , the display of pnr
7.Retrieve the cancelled Air and proceed to alternate fly date in such a way that new flight date is coming between the cruise sailing date .
8.Click on confirm .
9.From Home click on Tour ops
10.click on ops request button.
11.Select the request type as schedule_change and click on search.
12.Click on view history link
13.click on the plus icon with PNR
14.click the PNR link.
15.check the details.
16.Retrieve the PNR
17.Check the service request tab
ARGO-6019 | Verify the schedule change on a Package with air booking in which the checks are passed | 1.Navigate to Air->flight timing configuration-> Set a configuration for a Airport | 1.Go to the production | AIR | 1.Flight Definition screen_Pop up displayed in flight definition screen when occurs any cancellation of flight on particular day
|  | 2.Navigate to the settings->organisation settings->Air->booking->Set the time change limit, minimum connection time ,Maximum connection time,User acceptance as YES | 2.Air ->Negotiated Inventory |  | 2.Flight Operation screen_Check the Cancelled date bookings are retieved correctly and could do the schedule change. and get alternative flight confirm message.
|  | 3. Should have a booking Package with Air + cruise booking along with hotel if required. | 3.Search the for the flight |  | 3.Tour OPs Screen_Check the schedule changed status.
|  |  | 4.Change the schedule date in such way that it will cancel the flight on a particular day. |  | 4.Retrieve PNR_ check the details whether the schedule changed or not
5.Save the flight definition.
6.Go to Air-> Flight operation
7.Retrieve the cancelled Air and proceed to alternate fly date .
8.Click on confirm .
9.From Home click on Tour ops
10.click on ops request button.
11.Select the request type as schedule_change and click on search.
12.Click on view history link
13.click on the plus icon with PNR
14.click the PNR link.
15.check the details
16.Retrieve the PNR
ARGO-6019 | Verify the schedule change on a package with air booking in which the checks are failed. | 1.Navigate to Air->flight timing configuration-> Set a configuration for a Airport | 1.Go to the production | AIR | 1.Flight Definition screen_Pop up displayed in flight definition screen when occurs any cancellation of flight on particular day
|  | 2.Navigate to the settings->organisation settings->Air->booking->Set the time change limit, minimum connection time ,Maximum connection time,User acceptance as YES | 2.Air ->Negotiated Inventory |  | 2.Flight Operation screen_Check the Cancelled date bookings are retieved correctly and could do the schedule change. and get alternative flight confirm message.
|  | 3. Should have a booking Package with Air + cruise booking along with hotel if required. | 3.Search the for the flight |  | 3.Tour OPs Screen_Check the schedule changed status.
|  |  | 4.Change the schedule date in such way that it will cancel the flight on a particular day . |  | 4.Retrieve PNR_ check the details whether the schedule changed or not .
|  |  | 5.Save the flight definition. |  | 5.Service Request_Check the failed cases are available in service request
|  |  | 6.Go to Air-> Flight operation |  | 6.Hide flag_Check if hide is yes , the display of pnr
7.Retrieve the cancelled Air and proceed to alternate fly date in such a way that new flight date is coming between the cruise sailing date .
8.Click on confirm .
9.From Home click on Tour ops
10.click on ops request button.
11.Select the request type as schedule_change and click on search.
12.Click on view history link
13.click on the plus icon with PNR
14.click the PNR link.
15.check the details.
16.Retrieve the PNR
17.Check the service request tab
ARGO-6019 | Verify the schedule change on FIT Air in which schedule checks failed and do a re run | 1.Navigate to Air->flight timing configuration-> Set a configuration for a Airport | 1.Go to the production | AIR | 1.Flight Definition screen_Pop up displayed in flight definition screen when occurs any cancellation of flight on particular day
|  | 2.Navigate to the settings->organisation settings->Air->booking->Set the time change limit, minimum connection time ,Maximum connection time in such a way that it will fails the schedule checks and select the User acceptance as YES | 2.Air ->Negotiated Inventory |  | 2.Flight Operation screen_Check the Cancelled date bookings are retieved correctly and could do the schedule change. and get alternative flight confirm message.
|  | 3. Should have a booking Air + cruise booking along with hotel if required. | 3.Search the for the flight |  | 3.Tour OPs Screen_Check the schedule changed status.
|  |  | 4.Change the schedule date in such way that it will cancel the flight on a particular day . |  | 4.Retrieve PNR_ check the details whether the schedule changed or not .
|  |  | 5.Save the flight definition. |  | 5.Service Request_Check the failed cases are available in service request
|  |  | 6.Go to Air-> Flight operation |  | 6.Hide flag_Check if hide is yes , the display of pnr
|  |  | 7.Retrieve the cancelled Air and proceed to alternate fly date in such a way that new flight date is coming between the cruise sailing date . |  | 7.Should do the invoulantory /voluntory change on schedule after the failure
8.Click on confirm .
9.From Home click on Tour ops
10.click on ops request button.
11.Select the request type as schedule_change and click on search.
12.Click on view history link
13.click on the plus icon with PNR
14.click the PNR link.
15.check the details.
16.Retrieve the PNR
17.Check the service request tab
18.Got ot revise screen , amendment the OD for another offer which will pass the checks .
19.Proceed.
ARGO-6019 | Verify the Time change on a booking(FIT) in which the schedule checks are passed | 1.Navigate to Air->flight timing configuration-> Set a configuration for a Airport | 1.Navigate to Production>Products>Air>Negotiated Flight Inventory | AIR | 1.Flight Definition screen_when changing the time ,page should save without any interactions.
|  | 2.Navigate to the settings->organisation settings->Air->booking->Set the time change limit, minimum connection time ,Maximum connection time,User acceptance as YES | 2. Update the Departure Time and Arrival Time accordingly |  | 2. The PNR should be in workflow.
|  | 3. Should have a booking Package with Air + cruise booking along with hotel if required. | 4. Change/Update the Terminals, Checkin time & Equipment type |  | 3.Should able to run job.
|  |  | 5. Click on Save |  | 4.Retrieve PNR_ check the details whether the time changed with message '"The air item has undergone involuntary change (Completed)"'
6. Navigate to Production>Business Management>Workflows and Queues>Workflow Dashboard
7. Click on 'Air Schedule Change WF' link
8. Verify the booking reference number(PNR1) is listing under Air Schedule Change
9. Navigate to Production>Business Management>Scheduler>Scheduler Console
10. Create and run scheduler job under AirInvoluntaryScheduleChangeJob
11. Verify the process in AirInvoluntaryScheduleChangeJob is success
12. Navigate to Selling> Search and retrieve the booking reference number(PNR1)
13. Verify the updated details(Terminals,Checkin time,Equipment,Departure & Arrival Time) are reflected in Product details of existing booking" with below message
"The air item has undergone involuntary change (Completed)"
ARGO-6019 | Verify the Time change on a FIT booking in which the checks are failed. | 1.Navigate to Air->flight timing configuration-> Set a configuration for a Airport | 1.Navigate to Production>Products>Air>Negotiated Flight Inventory | AIR | 1.Flight Definition screen_when changing the time ,page should save without any interactions.
|  | 2.Navigate to the settings->organisation settings->Air->booking->Set the time change limit, minimum connection time ,Maximum connection time,User acceptance as YES | 2. Update the Departure Time and Arrival Time accordingly |  | 2. The PNR should be in workflow.
|  | 3. Should have a booking Package with Air + cruise booking along with hotel if required. | 4. Change/Update the Terminals, Checkin time & Equipment type |  | 3.Should able to run job.
|  |  | 5. Click on Save |  | 4.Retrieve PNR_ check the details whether the time changed with the message 'The air item has undergone involuntary change (User Acceptance required)'.
|  |  | 6. Navigate to Production>Business Management>Workflows and Queues>Workflow Dashboard |  | 5.Service Request_Check the failed cases are available in service request
|  |  | 7. Click on 'Air Schedule Change WF' link |  | 6.Hide flag_Check if hide is yes , the display of pnr
8. Verify the booking reference number(PNR1) is listing under Air Schedule Change
9. Navigate to Production>Business Management>Scheduler>Scheduler Console
10. Create and run scheduler job under AirInvoluntaryScheduleChangeJob
11. Verify the process in AirInvoluntaryScheduleChangeJob is success
12. Navigate to Selling> Search and retrieve the booking reference number(PNR1)
13. Verify the updated details(Terminals,Checkin time,Equipment,Departure & Arrival Time) are reflected in Product details of existing booking".
14.Check the details in Service request tab
15. Verify the user is notified against the air item with the below message
"The air item has undergone involuntary change (User Acceptance required)"
ARGO-6019 | Verify the Time change on a Package with air booking in which the checks are passed | 1.Navigate to Air->flight timing configuration-> Set a configuration for a Airport | 1.Navigate to Production>Products>Air>Negotiated Flight Inventory | AIR | 1.Flight Definition screen_when changing the time ,page should save without any interactions.
|  | 2.Navigate to the settings->organisation settings->Air->booking->Set the time change limit, minimum connection time ,Maximum connection time,User acceptance as YES | 2. Update the Departure Time and Arrival Time accordingly |  | 2. The PNR should be in workflow.
|  | 3. Should have a booking Package with Air + cruise booking along with hotel if required. | 4. Change/Update the Terminals, Checkin time & Equipment type |  | 3.Should able to run job.
|  |  | 5. Click on Save |  | 4.Retrieve PNR_ check the details whether the time changed with message '"The air item has undergone involuntary change (Completed)"'
6. Navigate to Production>Business Management>Workflows and Queues>Workflow Dashboard
7. Click on 'Air Schedule Change WF' link
8. Verify the booking reference number(PNR1) is listing under Air Schedule Change
9. Navigate to Production>Business Management>Scheduler>Scheduler Console
10. Create and run scheduler job under AirInvoluntaryScheduleChangeJob
11. Verify the process in AirInvoluntaryScheduleChangeJob is success
12. Navigate to Selling> Search and retrieve the booking reference number(PNR1)
13. Verify the updated details(Terminals,Checkin time,Equipment,Departure & Arrival Time) are reflected in Product details of existing booking with below message
"The air item has undergone involuntary change (Completed)"
ARGO-6019 | Verify the Time change on a package with air booking in which the checks are failed. | 1.Navigate to Air->flight timing configuration-> Set a configuration for a Airport | 1.Navigate to Production>Products>Air>Negotiated Flight Inventory | AIR | 1.Flight Definition screen_when changing the time ,page should save without any interactions.
|  | 2.Navigate to the settings->organisation settings->Air->booking->Set the time change limit, minimum connection time ,Maximum connection time,User acceptance as YES | 2. Update the Departure Time and Arrival Time accordingly |  | 2. The PNR should be in workflow.
|  | 3. Should have a booking Package with Air + cruise booking along with hotel if required. | 4. Change/Update the Terminals, Checkin time & Equipment type |  | 3.Should able to run job.
|  |  | 5. Click on Save |  | 4.Retrieve PNR_ check the details whether the time changed with the "The air item has undergone involuntary change (User Acceptance required)"
|  |  | 6. Navigate to Production>Business Management>Workflows and Queues>Workflow Dashboard |  | 5.Service Request_Check the failed cases are available in service request
|  |  | 7. Click on 'Air Schedule Change WF' link |  | 6.Hide flag_Check if hide is yes , the display of pnr
8. Verify the booking reference number(PNR1) is listing under Air Schedule Change
9. Navigate to Production>Business Management>Scheduler>Scheduler Console
10. Create and run scheduler job under AirInvoluntaryScheduleChangeJob
11. Verify the process in AirInvoluntaryScheduleChangeJob is success
12. Navigate to Selling> Search and retrieve the booking reference number(PNR1)
13. Verify the updated details(Terminals,Checkin time,Equipment,Departure & Arrival Time) are reflected in Product details of existing booking".
14.Check the details in Service request tab
15. Verify the user is notified against the air item with the below message
"The air item has undergone involuntary change (User Acceptance required)"
ARGO-6019 | Verify the schedule change on FIT Air in which schedule checks failed and do a re run | 1.Navigate to Air->flight timing configuration-> Set a configuration for a Airport | 1.Navigate to Production>Products>Air>Negotiated Flight Inventory | AIR | 1.Flight Definition screen_when changing the time ,page should save without any interactions.
|  | 2.Navigate to the settings->organisation settings->Air->booking->Set the time change limit, minimum connection time ,Maximum connection time,User acceptance as YES | 2. Update the Departure Time and Arrival Time accordingly |  | 2. The PNR should be in workflow.
|  | 3. Should have a booking Package with Air + cruise booking along with hotel if required. | 4. Change/Update the Terminals, Checkin time & Equipment type |  | 3.Should able to run job.
|  |  | 5. Click on Save |  | 4.Retrieve PNR_ check the details whether the time changed.
|  |  | 6. Navigate to Production>Business Management>Workflows and Queues>Workflow Dashboard |  | 5.Service Request_Check the failed cases are available in service request
|  |  | 7. Click on 'Air Schedule Change WF' link |  | 6.Hide flag_Check if hide is yes , the display of pnr
|  |  | 8. Verify the booking reference number(PNR1) is listing under Air Schedule Change |  | 7.Should do the invoulantory /voluntory change on schedule after the failure
9. Navigate to Production>Business Management>Scheduler>Scheduler Console
10. Create and run scheduler job under AirInvoluntaryScheduleChangeJob
11. Verify the process in AirInvoluntaryScheduleChangeJob is success
12. Navigate to Selling> Search and retrieve the booking reference number(PNR1)
13. Verify the updated details(Terminals,Checkin time,Equipment,Departure & Arrival Time) are reflected in Product details of existing booking".
14.Check the details in Service request tab
15. Verify the user is notified against the air item with the below message
"The air item has undergone involuntary change (User Acceptance required)"
16.Got ot revise screen , amendment the OD for another offer which will pass the checks .
17.Proceed.
ARGO-9568 | Verify user is able to apply surcharge for FIT Air with Rate Model = 'Cost and Price' and Cost basis is Amount and MarkupType is Percentage |  | "1. Navigate to Finance & Accounting --> Surcharges and Taxes | Payments & Surcharges
2. Add Surcharge/Tax
3. Provide all Mandatory Details. Rate Model = Cost and Price
4. Select Amount from Costbasis drop down and Percentage from Markup Type dropdown
5. Add valid data
4. Add Product
5. Choose Air product
6. Fill in Details
7. Save
8. Navigate to the Selling section and search for an air where the start date matches the travel start date and falls within the start and end date range (excluding the end date) specified in Surcharges and Taxes."""
ARGO-9568 | Create a surcharge for Air with zero price and verify it is not visible in booking/shopping |  | "1. Navigate to Finance & Accounting --> Surcharges and Taxes | Payments & Surcharges
2. Add Surcharge/Tax
3. Provide all Mandatory Details. Rate Model = Price
4. Select Amount from Costbasis drop down
5. Add zero amount
4. Add Product
5. Choose Air product
6. Fill in Details
7. Save
8. Navigate to the Selling section and search for an air"
ARGO-9568 | Label change: Verify label change from Night/Stay to Applied Per Night in 'Add Surcharge and Taxes' screen |  | 1. Login to iTravel Production url | Payments & Surcharges
2. Navigate to Finance and Accounting>>Surcharges and Taxes
3. Click on Add Surcharge/Tax
4.Add Surcharges and Taxes screen is displayed
5. Check the label Applied Per Night with a drop down Yes/No in Add Surcharges and Taxes screen>>General Info section (Earlier label was Night/Stay)
6. Verify applied per Night is selected as No by default"
ARGO-9568 | Verify the mandatory fields set in configuration screen is actually displayed as mandatory in Surcharge definition screen (Configuration screen is saved for Product Air and mandatory fields set is supplier |  | 1. Navigate to Surcharges and Taxes in Production site. | Payments & Surcharges
| ) |  | 2. Create new surcharge for cruise
3. Verify Product Applicability-Air
ARGO-9568 | Verify if user select value for Air route code in Product applicability Air in surcharge definition, then Origin, origin type, destination, destination type fields are disabled |  | 1. Navigate to Surcharges and Taxes in Production site. | Payments & Surcharges
2. Create new surcharge for Air
3. Add Product Applicability-Air
4. Origin type and Destination type field are initialy enabled
5. Add value for Air route code
ARGO-79952
ARGO-116322
ARGO-81276
ARGO-60141 | Create Cruise from List Cruise catalogue screen by enabling Auto generate Cruise ID Setting (Ship Code + Departure Date (MMDDYY) + Voyage Days (3 digits) |  | 1.Navigate to Product -> Cruise ->Definitions |  | Cruise code will be auto generated, Cruise will get saved as per details given
2. Click on Add New Button on List Cruise catalogue Screen
3.Fill the details and save
Note -Auto generate cruise ID setting should be enabled with attributes "Ship Code + Departure Date (MMDDYY) + Voyage Days (3 digits)"
ARGO-60141 | Create Cruise from List Cruise catalogue screen by disabling Auto generate Cruise ID Setting |  | 1.Navigate to Product -> Cruise ->Definitions |  | Cruise Code wont be auto generated, Cruise will get saved as per details given
2. Click on Add New Button on List Cruise catalogue Screen
3.Fill the details and save
Note -Auto generate cruise ID setting should be disabled
ARGO-60141 | Propagate cruise by enabling Auto generate Cruise ID Setting (Ship Code + Departure Date (MMDDYY) + Voyage Days (3 digits) |  | 1.Navigate to Product -> Cruise ->Definitions |  | Cruise Code should be generated as per attribute order <<ShipcodeDDMMYYVN>> with correct details .
2. Search for Cruise
3.Select any valid cruise
4. Click on Propagate
5. Propagate Cruise window will be displayed
6. Choose Start date ,End After and Interval
Note -Auto generate cruise ID setting should be enabled with attributes "Ship Code + Departure Date (MMDDYY) + Voyage Days (3 digits)"
7.click on Preview
Note :
2)Interval will be enabled if the end after is greater than 1
ARGO-60141 | Create Cruise through excel upload by enabling Auto generate Cruise ID Setting (Ship Code + Departure Date (MMDDYY) + Voyage Days (3 digits) |  | 1. Fill the valid data as per Precondition and save the template |  | Cruise Code should be generated as per attribute order <<ShipcodeDDMMYYVN>> with correct details and visible in List Cruise Catalogue screen.
2.Navigate to Product -> Cruise ->Definitions
|  |  | 3.Click on Upload Data |  | And if duplicate cruise code exist .. Error file should be generated with proper error
4. Browse the template and Click on Upload
5. File should be processed successfully
6. Navigate to List Cruise catalogue and Verify the newly created cruise as per template
Note -Auto generate cruise ID setting should be enabled with attributes "Ship Code + Departure Date (MMDDYY) + Voyage Days (3 digits)"
ARGO-60141 | Create Cruise through ship deployment screen enabling Auto generate Cruise ID Setting (Ship Code + Departure Date (MMDDYY) + Voyage Days (3 digits) |  | 1.Navigate to Product -> Cruise ->Cruise Operations->Ship deployment |  | Cruise Code should be generated as per attribute order <<ShipcodeDDMMYYVN>> with correct details
2.Select the ship , From and To date on Ship deployment schedule screen
3.Click on side navigator ->choose Itinerary code and search
4.Select the Itinerary and Drag
5. Itinerary port will be listed
6.Click on green tick mark
7.Commit Cruise Popup will be displayed with relevant details
Note -Auto generate cruise ID setting should be enabled with attributes "Ship Code + Departure Date (MMDDYY) + Voyage Days (3 digits)"
ARGO-48320 | Configure only Role in "Access for Manual Credit granting" section in the template and verify user logged in with same Role can view and grant credit |  | 1.Navigate to Tactical sales and Marketing->credit template |  | System should display configured credit templayte in Grant credit pop up and able to grant credit without any issue
2.Configure Role in Access for Manual credit granting section
3.Login as a user into the application with matching Role configured
4.Try to Grant credit from Customer/Agency entitlement or Booking confirmation and check same credit template displays in Grant pop up
5.Verify user can Grant the credit template
ARGO-48320 | Configure only Users(Include) in "Access for Manual Credit granting" section in the template and loggin as same user and verify user can view and grant credit |  | 1.Navigate to Tactical sales and Marketing->credit template |  | System should display configured credit templayte in Grant credit pop up and able to grant credit without any issue
2.Configure only Users(Include) in Access for Manual credit granting section
3.Login into the application with same user
4.Click on Grant credit from Customer/Agency entitlement or Booking confirmation and check same credit template displays in Grant pop up
5.Verify user can Grant the credit template
ARGO-48320 | Configure Role and Users (Exclude) in "Access for Manual Credit granting" section in the template and login with the user having matching role and user added in Users (Exclude) and verify user cannot view and grant the credit |  | 1.Navigate to Tactical sales and Marketing->credit template |  | System should not display the credit template in Grant credit pop up as user added in Users(Exclude)
2.Configure Role and Users(Exclude) in Access for Manual credit granting section
3.Login as a user with matching role but user added in Users(Exclude)
4.Click on Grant credit from Customer/Agency entitlement or Booking confirmation and check same credit template displays in Grant pop up
5.Verify user can Grant the credit template
ARGO-6251 | Verify user is able to create booking for flexible package with cruise as Lead item for an Allocated Agency Group | 1. An allocated Agency group is created and a flexible package with a lead cruise is added and saved for the group. | 1. Navigate to selling app. | GROUPS | User should be able to complete booking for a allocated Agency Group.
|  | 2.Allocation for a category for a rate plan is allocated. | 2. Search and load the agency |  | Sold count should be updated in the Group package static block in Cruise inventory
|  | 3. Agency commission defined for Cruise product applicable for CAB charges | 3. Select New Group booking |  | Sold count should be updated against the category in the Allocation section of Allotment and Pricing screen
|  | 4.Group is in Active status. | 4. Search for group code and Proceed |  | Total Sold and Booked count should be updated for categories in the Summary section of Allotment and Pricing screen
|  | 5.Group Occupancy Master and Occupancy control for the 6.Group catalogue should be configured with occupancycode, passengers - 1A,2A,3A,4A for PKG product type | 5. Proceed with Group listing
|  | 7.Package rate plan should be set up with Price methodology - Roll-up pricing and Price opacity -Transparent. | 4. Select 2A from Shop Package Select Passenger pop-up and proceed
|  | 8.Cruise rate plans applicable for the Group should exist. | 5. Select the cabin category/ Auto Assign and continue
|  | 9.Applicable block in cruise inventory has Group source and Package source set to Yes | 6. Load Passenger profiles and proceed
7. Journey planner screen should be displayed
8. Proceed to Review cart screen
9. Provide Passenger info save and continue
10. Complete the payment.
ARGO-6251 | Verify user is able to create booking for flexible package with cruise as Lead item for a non Allocated Agency Group | 1. A non allocated Agency group is created and a flexible package with a lead cruise is added and saved for the group. | 1. Navigate to selling app. | GROUPS | User should be able to complete booking for a non allocated Agency Group
|  | 2.Inventory is requested for a category. | 2. Search and load the agency |  | Sold count should be updated in the applicable block in Cruise inventory
|  | 3. Agency commission defined for Cruise product applicable for CAB charges | 3. Select New Group booking |  | Sold count should be updated against the category in the Allocation section of Allotment and Pricing screen
|  | 4.Group is in Active status. | 4. Search for group code and Proceed
|  | 5.Group Occupancy Master and Occupancy control for the 6.Group catalogue should be configured with occupancycode, passengers - 1A,2A,3A,4A for PKG product type | 5. Proceed with Group listing
|  | 7.Package rate plan should be set up with Price methodology - Roll-up pricing and Price opacity -Transparent. | 4. Select 2A from Shop Package Select Passenger pop-up and proceed
|  | 8.Cruise rate plans applicable for the Group should exist. | 5. Select the cabin category/ Auto Assign and continue
|  | 9.Applicable block in cruise inventory has Group source and Package source set to Yes | 6. Load Passenger profiles and proceed
7. Journey planner screen should be displayed
8. Proceed to Review cart screen
9. Provide Passenger info save and continue
10. Complete the payment.
ARGO-6251 | Verify user is able to create on option booking for flexible package with cruise as Lead item for a non Allocated Direct Group | 1. A non allocated Agency group is created and a flexible package with a lead cruise is added and saved for the group. | 1. Navigate to selling app. | GROUPS | User should be able to complete booking for a non allocated Agency Group
|  | 2.Inventory is requested for a category. | 2. Search and load the agency |  | Sold count should be updated in the applicable block in Cruise inventory
|  | 3. Agency commission defined for Cruise product applicable for CAB charges | 3. Select New Group booking |  | Sold count should be updated against the category in the Allocation section of Allotment and Pricing screen
|  | 4.Group is in Active status. | 4. Search for group code and Proceed
|  | 5.Group Occupancy Master and Occupancy control for the 6.Group catalogue should be configured with occupancycode, passengers - 1A,2A,3A,4A for PKG product type | 5. Proceed with Group listing
|  | 7.Package rate plan should be set up with Price methodology - Roll-up pricing and Price opacity -Transparent. | 4. Select 2A from Shop Package Select Passenger pop-up and proceed
|  | 8.Cruise rate plans applicable for the Group should exist. | 5. Select the cabin category/ Auto Assign and continue
|  | 9.Applicable block in cruise inventory has Group source and Package source set to Yes | 6. Load Passenger profiles and proceed
7. Journey planner screen should be displayed
8. Proceed to Review cart screen
9. Provide Passenger info save and continue
10. From payment screen update the payment to a future date
ARGO-6251 | Verify user is able to create booking for flexible package with cruise as Lead item for an Allocated Direct Group for 2A1C1I | 1. An allocated Direct group is created and a flexible package with a lead cruise is added and saved for the group. | 1. Navigate to selling app. | GROUPS | User should be able to complete booking for a allocated Group.
|  | 2.Allocation for a category for a rate plan is allocated. | 2. Select New Group booking |  | Sold count should be updated in the Group package static block in Cruise inventory
|  | 3.Group is in Active status. | 3. Search for group code and Proceed |  | Sold count should be updated against the category in the Allocation section of Allotment and Pricing screen
|  | 4.Group Occupancy Master and Occupancy control for the 5.Group catalogue should be configured with occupancycode, passengers - 1A,2A,3A,4A for PKG product type | 4. Proceed with Group listing |  | Total Sold and Booked count should be updated for categories in the Summary section of Allotment and Pricing screen
|  | 6.Package rate plan should be set up with Price methodology - Roll-up pricing and Price opacity -Transparent. | 5. Select 2A1C1I from Shop Package Select Passenger pop-up and proceed
|  | 7.Cruise rate plans applicable for the Group should exist. | 6. Select the cabin category/ Auto Assign and continue
|  | 8.Applicable block in cruise inventory has Group source and Package source set to Yes | 7. Load Passenger profiles and proceed
8. Journey planner screen should be displayed
9. Proceed to Review cart screen
10. Provide Passenger info save and continue
11. Complete the payment.

## Summary
|  | Automation Status | No | Automation Status | Yes
Owner | Count of Smoke Scenarios | Status | Count of Smoke Scenarios | Status | Count of Smoke Scenarios
Akshay | 35 | Not Started | 1.695% | Not Started | 1.681%
Drisya | 35 | Pass | 85.31% | Pass | 97.9%
Gracy | 35 | Blocked | 1.13% | Fail | 0.4202%
Greeshma | 35 | Fail | 11.86% | Grand Total | 100%
Kavitha | 35 | Grand Total | 100%
Merin | 35
Shine | 35
Neethi | 38
Grand Total | 283

## Bugs Reported
No. | Bugs | Priority | Reporter
| ITRVL34RCG-49667 - STAGE Smoke 16/01 - Unable to attach and save documents due to an error in the booking attachment. | Critical | Greeshma | New
| ITRVL34RCG-48763 : Staging Smoke (09/01) - In Customize and Shuffle window all of the categories shows the same price | Major | Drisya | Existing
| ITRVL34RCG-48764 : Stage Smoke (09/01) - Warning message duplicated when excludable item availability changed | Major | Drisya | Existing
| ITRVL34RCG-46468 : SIT2 Smoke 09/12 - Categories in Hotel item are duplicated in customize window | Major | Drisya | Existing
| ITRVL34-215319 : Stage Smoke 30/12 - Invalid Error Message Displayed when providing pax info in the pax popup before review cart | Major | Drisya | Existing
| ITRVL34RCG-47190: SIT1_SMOKE (17/12) – Booking Level and Pax Level Attachments are Not Saving | critical | Akshay | Existing
| ITRVL34RCG-48389 - Stage Smoke 05/01 - Groups - Currencies fail to load for the "EUR" market | Major | Greeshma | Existing
| ITRVL34RCG-40552 - STAGE Smoke 10/10 - Not able to one click remove pax or split pax in an AIR booking | Critical | Geethu George | Existing
| ITRVL34RCG-47239- SIT1 Smoke 17/12 - Air surcharges are not applied for air routes in selling | Critical | Shine | Existing
| ITRVL34RCG-48808 : - Smoke_Stage(09/01) - Brand master excel download - The status information is incorrectly populated in the MetaTags instead of the status field | Major | Akshay | Existing
| ITRVL34RCG-49681:-STAGE-Smoke 16/01 - Standard and bonus commission are not reflecting in selling | Critical | Akshay | New
| ITRVL34RCG-49683 : STAGE Smoke 16/01 - Unable to change flight schedule for a flight having bookings | Critical | Shine | New
| ITRVL34RCG-40937 - Re-run Schedule Change Checks on Failed Air Items and During Modifications got failed | Critical | Glady Anto | Existing
| ITRVL34RCG-49686 - Stage_Smoke 16/10 - Cannot Upload Deckplan | Critical | Akshay | New
| ITRVL34-215323 -Smoke-Stage-31/12-Group Catalogue Search – Travel Start Date field remains marked as mandatory (red) even after entering a valid date | Major | Akshay | Existing
| ITRVL34RCG-46066 -Stage_Smoke (05/12) – Cabin Rates: Unable to modify the cabin rates. System displays the error: “The rate set code is not valid for the given applicability condition.” | Critical | Akshay | Existing
| ITRVL34RCG-47923 :SIT1 Smoke 24/12 - Cannot Cancel Air Booking | Critical | Drisya | Existing
| ITRVL34RCG-49358 : SIT1 Smoke 14/01 - Commission refund process batch jobs for "Posted" status are still in pending | Critical | Shine | Existing
| ITRVL34RCG-49059 : Stage smoke 12/01 - Transaction silently rolled back error is getting while trying to create transfer | Blocker | Merin | Existing
| ITRVL34RCG-49707 - Stage_Smoke-16/10 -Cruise amendments are not functioning even though the amendment rule is being picked up | Major | Akshay | New
| ITRVL34RCG-47919 : Smoke-SIT1 -24/12- Cruise Amendment – Cabin amendment charge is not applying even though the rule is picked correctly | Critical | Akshay | Existing
| ITRVL34-215518 - While applying promotion from booking confirmation screen, getting error message Cabin is on hold. and promotion not applied | Critical | Geethu George | Existing
| ITRVL34RCG-49718 -STAGE Smoke 16/01 - Agent page is not showing (displays "Access Denied") even though the privileges for agents are enabled | Critical | Neethi | New
| ITRVL34RCG-49690 - STAGE Smoke 16/01- Save button is not seen when a new Agency is added from Agency Definition | Critical | Neethi | New